## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Nithya | 2025-10-23 | Live speech transcription misses or misinterprets words during fast-paced conversations | 1 | Nithya | Logical | Tuned Gemini Live transcription parameters and optimized audio chunk handling to better support fast speech | 2025-10-21 | Closed | Issue mainly observed with rapid speaker delivery
2 | Nithya | 2025-11-06 | Delay in converting long audio recordings into text during upload analysis | 1 | Nithya | Standards | Optimized audio preprocessing pipeline and reduced latency in batch transcription flow | 2025-10-22 | Closed | Delay noticeable for audio files longer than 5 minutes
3 | Nithya | 28-Oct-0205 | Background noise affects transcription accuracy in recorded calls | 2 | Nithya | Logical | Added noise suppression and improved audio filtering before sending data to Gemini Live API | 2025-11-01 | Closed | Issue more frequent in noisy environments
4 | Nithya | 2025-11-19 | Speaker diarization fails to correctly distinguish between multiple speakers | 2 | Nithya | Logical | Upgraded diarization logic and aligned Python audio processing with compatible library versions | 2025-11-09 | Closed | Caused by version mismatch between audio libs
5 | Nithya | 2025-11-19 | System fails to accurately extract entities from transcribed call data | 3 | Nithya | Logical | Enhanced entity extraction rules and refined Gemini prompt instructions for structured outputs | 2025-11-15 | Closed | Errors mostly observed for uncommon names
6 | Nithya | 2025-12-05 | AI suggestions are not updated in real time based on latest customer responses | 4 | Nithya | Maintainability | Optimized real-time response pipeline and improved streaming update handling | 2025-12-01 | Closed | Minor lag when switching between speakers

## Sheet2
Logical
User Interface
Maintainability
Standards
Others