## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Nithya | 2025-10-23 | Collection of Minimum 2 minutes audio | 1 | Nithya | Data | Creation of dataset | 2025-10-24 | Closed | Necessary for project
2 | Nithya | 2025-11-06 | Speaker Diarization in audio to text | 1 | Nithya | Code | Changed to two Speaker transcript | 2025-11-07 | Closed | Add two speaker
3 | Nithya | 28-Oct-0205 | Agile Documentation | 1 | Nithya | Document | Correction in sheets | 2025-11-28 | Closed | About Id's in the sheets
4 | Nithya | 2025-11-19 | Live Speech to text | 2 | Nithya | Code | Added two speaker | 2025-11-21 | Closed | Add two speakers and make it real time
5 | Nithya | 2025-11-19 | UI addition | 2 | Nithya | Code | Added UI | 2025-11-23 | Closed | Add a UI to the project
6 | Nithya | 2025-12-05 | Intent analysis, Emotion detection | 3 | Nithya | code | Added special detection to customer texts | 2025-12-06 | Closed | Found error and got suggestion to resolve